## Slide 1
CLIENT WORKING SESSION
Stabilising public cloud
provisioning and decommissioning
Findings, joint improvement priorities and decisions required
Discussion draft | 23 August 2026
Notes: [Sources]
- User-supplied current-state process and meeting request; meeting date and attendees were not Calendar-verified.
- No external claims are used on this slide.

## Slide 2
PUBLIC CLOUD PROCESS IMPROVEMENT
Flow constraints—not effort—are driving the backlog
2
Assignment starts before readiness is proven, ownership is locked, and waiting time is hidden inside the delivery SLA.
96
managed backlog
81
already executing
15
processing / ready
2–42
projected load range
vs. 12-point capacity
What this means
The current queue mixes active work with requestor, access and infra waiting. Capacity appears consumed even when engineers cannot progress, while actual work is distributed unevenly.
Source: Task Control Hub snapshot dated 20 Aug 2026; workload points are provisional.
Notes: [Sources]
- CSSP Task Control Hub, Dashboard A6:M29 and Engineer Capacity A4:O15, snapshot dated 20 August 2026.
- Interpretation is based on the user-supplied process description and feedback.

## Slide 3
PUBLIC CLOUD PROCESS IMPROVEMENT
Five control gaps create avoidable waiting and rework
3
The issues span platform design, operating controls and cross-team governance—not only engineering execution.
Control gap | Observed effect | Operational risk
CSSP assignment and visibility | SLA starts early; owner locks; no requester-visible progress | Unmanaged ageing and fragile ownership
Readiness and scope baseline | Missing access or details; scope changes remain in email | Rework, disputes and forecast churn
External approval control | Infra approvals wait without response commitment | SLA breach without clear accountable owner
Activity-level history | One ticket status overwrites concurrent activity states | No auditable wait, rework or handover history
Decommission safeguards | Manual deletion; incomplete inventory, retention and drift controls | Wrong deletion, data loss or Terraform recreation
Finding: the process lacks a shared control model for readiness, work, waiting, approval and evidence.
Notes: [Sources]
- User-supplied current-state provisioning and decommissioning process.
- Feedback to Improve.xlsx, Sheet1 A1:E14.
- CSSP Task Control Hub, Task Master A4:Z10 and Engineer Updates A4:Q85.

## Slide 4
PUBLIC CLOUD PROCESS IMPROVEMENT
Ticket-level status cannot preserve activity history
4
One request contains multiple activities; every activity retains each status event.
REQUEST
CSSP12345
ACTIVITY REGISTER
A01
Repository access
Waiting access
A02
IaC scripting
In progress
A03
Infra approval
Not started
APPEND-ONLY EVENT HISTORY
09:00
Created
Not started
11:30
Submitted
Waiting – Infra
Next
Approved / rejected
Retained event
Current state is derived from the latest event. Earlier statuses, blockers, reassignment and scope changes are never overwritten.
Notes: [Sources]
- CSSP Task Control Hub, current ticket-level design in Task Master A4:Z10 and Engineer Updates A4:Q85.
- Activity-event model is a proposed control design based on user feedback; examples are illustrative.

## Slide 5
PUBLIC CLOUD PROCESS IMPROVEMENT
The target flow separates readiness, delivery and waiting time
5
The objective is not to pause service—it is to make ownership, blockers and decisions visible before irreversible assignment or deletion.
1
Intake
Scope + owner
2
Ready gate
Access + data
3
Prioritise
Impact + age
4
Assign
Capacity + backup
5
Plan
IaC / decom pack
6
Approve
Decision + window
7
Execute
Validate + close
WAITING IS A CONTROLLED STATE
Every blocker records an owner, pending-since time, next follow-up and escalation date. Gross SLA remains visible while active engineering and external waiting are measured separately.
Blue stages require client-owned platform or governance enablement.
Notes: [Sources]
- Proposed target operating model derived from the user-supplied current-state flow and feedback.
- Blue-stage ownership is proposed for client discussion and is not an existing commitment.

## Slide 6
DECISIONS REQUIRING CLIENT OWNERSHIP
Five client-owned changes unlock sustainable control
6
These are enabling changes the delivery team cannot implement alone. Priority indicates the recommended sequence for joint review.
Area | Requested client change | Outcome | Priority
CSSP | Visible triage/pending stages; pending reason and next-update date; team reassignment or queue ownership | Transparent progress and continuity | P0
BMC | Pending reasons; blocker owner; next-review date; structured work-note fields | Auditable waiting and escalation | P0
Infra approval | Response targets, approval clinics and named escalation path | Predictable decision cycle | P0
Information access | ADO access readiness; cloud inventory; CMDB extract or owner attestation | Reliable scope and dependency checks | P1
Governance | Approved retention, backup, restore and deletion-control standard | Safe, authorised decommissioning | P1
Meeting ask: nominate one accountable owner for each row and agree a feasibility date.
Notes: [Sources]
- Requested changes respond directly to the limitations documented in Feedback to Improve.xlsx, Sheet1 E2:E14.
- Priorities are recommendations for discussion; no client commitment is implied.

## Slide 7
CHANGES WITHIN DELIVERY-TEAM CONTROL
The delivery team will tighten execution and evidence
7
These controls can begin immediately while CSSP and BMC improvements are assessed.
OPERATING CONTROLS
• Readiness checklist before assignment
• Versioned scope within the same CSSP ticket
• WIP limit plus stage-weighted workload
• Standard infra approval package
• Two-person decommission verification
TRACKER REDESIGN
• Request → Activity → Event history
• Append-only status changes and handovers
• Automatic follow-up queue for due blockers
• Active time separated from external waiting
• Standard requester status message
Guardrail: Excel is interim. Version history and protected formula sheets are required until the log moves to a workflow platform.
Notes: [Sources]
- Proposed delivery controls based on the user-supplied current-state flow and feedback.
- Current interim tracker structure: CSSP Task Control Hub, Task Master A4:Z10 and Engineer Updates A4:Q85.

## Slide 8
PUBLIC CLOUD PROCESS IMPROVEMENT
A 90-day plan stabilises the queue
8
Delivery controls start now while client-owned platform and governance decisions progress.
0–14 DAYS
Stabilise
Reconfirm old scope
Classify blockers
Set WIP limits
Start status cadence
15–45 DAYS
Control
Launch activity/event log
Pilot approval OLA
Use standard packs
Measure wait time
46–90 DAYS
Embed
Prioritise CSSP/BMC changes
Approve retention standard
Baseline reporting
Review effectiveness
Success measure: fewer unowned blockers, lower active WIP, faster approval decisions and a complete activity-level audit trail.
Notes: [Sources]
- Proposed implementation sequence derived from the current-state findings; dates are relative and require joint agreement.
- No benchmark performance commitments are asserted.

## Slide 9
PROPOSED MEETING OUTCOMES
Today’s decisions define the next operating baseline
9
The meeting should close with named owners and dates—not only agreement that the issues exist.
1
Confirm a sponsor and feasibility review for CSSP changes
2
Agree the interim requester-status channel and cadence
3
Nominate BMC, CMDB/inventory and infra-approval owners
4
Approve a two-week OLA and activity-tracker pilot
5
Commission the retention, backup and deletion-control standard
Proposed next step: launch a two-week joint stabilisation sprint, then review the baseline with evidence.
Notes: [Sources]
- Proposed meeting decisions based on the user-supplied current-state assessment and feedback.
- Owners and dates remain open for confirmation during the client meeting.